## Sheet1
Item	COTS / Custom?	Number for Proto DUNE 2	Far Detector (common)	Number per SP Cavern	Spares	Total	Time to test each module/ staff-days	Total time to test	Notes
Micro TCA crate.	COTS	1		2	1	6	0.2	1.2	Chassis, JSM, MCH, PSU, Fans
GPS Discipled oscillator	COTS	1	2			3	0.2	0.6
GPS Interface Board (GIB)	Custom	1	2		1	4	1	4
Micro TCA Interface Board (MIB)	Custom	1		2	1	6	2	12
Micro TCA AMC FMC carriers	COTS	1		20	1	42	0.2	8.4
Fibre Interface Board (FIB)	Custom	2		20	4	46	0.1	4.6	10 per crate

							Total time to test all items	30.8

## Sheet2
Item	Total Number	Time to test each module/ staff-days	Total time to test / staff-days
Micro TCA crate.	6	0.2	1.2
GPS Discipled oscillator	3	0.2	0.6
GPS Interface Board (GIB)	4	1	4
Micro TCA Interface Board (MIB)	6	2	12
Micro TCA AMC FMC carriers	42	0.2	8.4
Fibre Interface Board (FIB)	46	0.1	4.6

Total time to test (staff days)			30.8

## Sheet3
Item	Estimated lead-time / days
Micro TCA crate.	14
GPS Discipled oscillator	14
GPS Interface Board (GIB)	30
Micro TCA Interface Board (MIB)	30
Micro TCA AMC FMC carriers	20
Fibre Interface Board (FIB)	30